## Sheet1
Project Initiatives | Catergory | Stategic Impact | Financial Impact | Risk | Oppurtunities for early success | Allignment with current initiatives | Resource Requirements | Dependency | Overall Priority Rank
1. SCBS | Business | H | H | H | L | M | H | M | H-3
2. VCMS | Business | H | H | H | M | M | H | M | H-2
3. Shipment Tracking (ShipTrack System) | Business | H | M | M | M | L | H | M | H-4
4. ESB | Solution | M | L | M | M | L | L | H | H-1
5. MQ for HRS | Technical | L | L | L | H | H | L | M | L-8
6. MQ for AFIS | Technical | L | L | L | H | H | L | M | L-9
7. Interface Engine | Solution | M | L | M | H | L | M | H | M-5
8. Web Portal | Information | M | L | M | H | M | M | H | M-6
9. Management Reports | Infromation | M | M | M | H | M | M | M | M-7

## Sheet2
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Capital Cost (Infrastructure) | 55000 | 0 | 0 | 0 | 0
Capital Cost (Development) | 369600 | 0 | 0 | 0 | 0
Yearly Maintenance Cost | 10000 | 10000 | 10000 | 10000 | 10000
Savings | 0 | 162400 | 182400 | 182400 | 222400
Expences | 434600 | 282200 | 109800 | -62600 | -275000