## Project Prioritization
Project Initiatives | Catergory | Stategic Impact | Financial Impact | Risk | Oppurtunities for early success | Allignment with current initiatives | Resource Requirements | Dependency | Overall Priority Rank
1. SCBS | Business | H | H | H | L | M | H | M | H-3
2. VCMS | Business | H | H | H | M | M | H | M | H-2
3. Shipment Tracking (ShipTrack System) | Business | H | M | M | M | L | H | M | H-4
4. ESB | Solution | M | L | M | M | L | L | H | H-1
5. MQ for HRS | Technical | L | L | L | H | H | L | M | L-8
6. MQ for AFIS | Technical | L | L | L | H | H | L | M | L-9
7. Interface Engine | Solution | M | L | M | H | L | M | H | M-5
8. Web Portal | Information | M | L | M | H | M | M | H | M-6
9. Management Reports | Infromation | M | M | M | H | M | M | M | M-7

## ROI - Summary
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Capital Cost (Infrastructure) | 55000 | 0 | 0 | 0 | 0
Capital Cost (Development) | 369600 | 0 | 0 | 0 | 0
Yearly Maintenance Cost | 10000 | 10000 | 10000 | 10000 | 10000
Savings | 0 | 162400 | 182400 | 202400 | 222400
Expenses | 434600 | 282200 | 109800 | -82600 | -295000
ROI | 0 | 0 | 0 | 82600 | 295000

## Project Bubble
Project | Risk | Value | Size
SCBS | 3 | 64800 | 2880
VCMS | 2 | 43200 | 3840
ShipTrack | 4 | 14400 | 960
ESB | 1 | 10000 | 480
MQ-HRS | 8 | 5000 | 240
MQ-AFIS | 9 | 5000 | 240
IE | 5 | 10000 | 640
WP | 6 | 10000 | 640
MR | 7 | 10000 | 640

## Transition Schedule - Ownership
| Projects | Ownership
Phase 1 | ESB | IT/Operations
| VCMS | Container Management Team
| IE | IT/Operations
| Web portal | Container Management Team
| Reports | Container Management Team
Phase 2 | SCBS | Order Processing Team
| ShipTrack | Order Processing Team
| IE | IT/Operations
| Web portal | Order Processing Team
| Reports | Order Processing Team
Phase 3 | MQ HRS | HR & Finance Team
| MQ AFIS | HR & Finance Team
| IE | IT/Operations
| Web portal | HR & Finance Team
| Reports | HR & Finance Team